## Summary
Notes: | This is a template only. You may edit anything to better suit your project.
For unit of measure, use Hours, and don't get more granular than 0.5 hours (e.g. If something took 1 hour 15 minutes, round up to 1.5 hours)
Note: | Provide Rough Order of Magnitude (high-level) estimates for these categories at the beginning of the project. You will not be evaluated on how close your estimates are.
|  | ROM | Estimate | Actual | Variance (hours) | Variance (%)
Project Management |  | 70 | 40 | 49 | -9 | 81.6327
| Meetings |  | 26 | 27 | -1 | 96.2963
| Other communication |  | 9 | 17 | -8 | 52.9412
| Documentation |  | 39 | 45 | -6 | 86.6667
Development |  | 40 | 329 | 404 | -75 | 81.4356
| Discussions with client |  | 9 | 17 | 0.5
| Creating prototype |  | 2 | 5 | 2
| Set up React Project |  | 1 | 2
| Study React.js |  | 10 | 30
| Creating prototype |  | 7 | 10
| Genral Coding |  | 300 | 340
Testing |  | 40 | 40 | 45 | -5 | 88.8889
| Genral Testing |  | 40 | 45
Integration & Deployment |  | 10 | 7 | 5 | 2 | 140

## Weekly
For certain tasks, track of time weekly, and summarize the total time on the first tab.
Do this for PM tasks, and optionally for other tasks that span multiple weeks.
|  | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13
Project Management
| Meetings | 3.5 | 3 | 2.5 | 2 | 2 | 3 | 3 | 0 | 3 | 3 | 3 | 3 | 3
| Other communication | 2 | 2 | 1.5 | 1.5 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 2 | 2
| Documentation | 4 | 4.5 | 7 | 3 | 3 | 6 | 3 | 3 | 2 | 1.5 | 4 | 3 | 3
| Discussions with client | 3.5 | 2 | 2 | 1 | 1 | 1 | 2 | 0 | 2 | 1 | 1 | 1 | 1
| Creating wirefarme | W1: 0; W2: 3; W3: 1; W4: 0
| Create prototype | W4: 6
| Study React.js |  |  | 5 | 15 |  | 5 | 4 | 6 | 4 | 5 | 3 | 7 | 4
| Set up React Project | W4: 2
| Create the detailed service panel |  |  |  |  | 2.5 | 1.5 | 10 | 10 | 12 | 15 | 14 | 20 | 10
| Create the desktop version of the application index |  |  |  |  | 1.5 | 2 | 2.5 | 12 | 10 | 10 | 28 | 29 | 10
| Apply some styles on the page |  |  |  |  | 1.5 | 2 | 2 | 2 | 2 | 1.5 | 6 | 1 | 12
| Make the transition between panel smoother |  |  |  |  | 0.5 | 2 | 2 | 1.5 | 2 | 2 | 3 | 3 | 2
| Search for better solution of desktop and mobile difference |  |  |  |  | 1 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 4
| Take notes during all the meetings |  |  |  |  | 1.5 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 1
| Weekly status report |  |  |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
| Weekly Meeting minutes (Client) |  |  |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
| Weekly Meeting minutes (Team) |  |  |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
| Weekly Meeting minutes (Supervisor) |  |  |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
| Weekly Risks & Technical Issues table |  |  |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
| Weekly Estimates and Actuals Tracking |  |  |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5