## Summary
Notes: | This is a template only. You may edit anything to better suit your project.
For unit of measure, use Hours, and don't get more granular than 0.5 hours (e.g. If something took 1 hour 15 minutes, round up to 1.5 hours)
Note: | Provide Rough Order of Magnitude (high-level) estimates for these categories at the beginning of the project. You will not be evaluated on how close your estimates are.
|  | ROM | Estimate | Actual | Variance (hours) | Variance (%)
Project Management |  | 70 | 11 | 9.5 | 1.5 | 115.7895
| Meetings |  | 4 | 3.5 | 0.5 | 114.2857
| Other communication |  | 3 | 2 | 1 | 150
| Documentation |  | 4 | 4 | 0 | 100
Development |  | 40 | 20 | 8.5 | 11.5 | 235.2941
| Discussions with client |  | 4 | 3.5 | 0.5
| Creating prototype |  | 5 | 3 | 2
| Set up React Project |  | 1 | 2
| Study React.js |  | 10 | 15
Testing |  | 40 | 0 | 0 | 0 | #DIV/0!
Integration & Deployment |  | 10 | 0 | 0 | 0 | #DIV/0!

## Weekly
For certain tasks, track of time weekly, and summarize the total time on the first tab.
Do this for PM tasks, and optionally for other tasks that span multiple weeks.
|  | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12
Project Management
| Meetings | W1: 3.5; W2: 3; W3: 2.5; W4: 2
| Other communication | W1: 2; W2: 2; W3: 1.5; W4: 1.5
| Documentation | W1: 4; W2: 4.5; W3: 7; W4: 3
| Discussions with client | W1: 3.5; W2: 2; W3: 2; W4: 1
| Creating wirefarme | W1: 0; W2: 3; W3: 1; W4: 0
| Create prototype | W4: 6
| Study React.js | W3: 5; W4: 15
| Set up React Project | W4: 2